THE PLAN – Draft 1

July 21-30 : prepare materials, practice on Pteropus at zoo?

July 31 – August 18: Moramanga sites

2 Argos GPS solar at Analambotaka

X e-obs at smaller metapopulations in the area

Aug 18 – 20: Tana

Aug 21 – 23: travel to Ankarana

Aug 23 – 1: Ankarana

2 Argos GPS solar

Any e-obs?

Sept 2-3: Travel to Nosy Hara

Sept 4 – 15: Nosy Hara

2 Argos GPS solar

2 Argos GPS battery (eidolon)

Any e-obs?

Sept 16-18: travel to Tana

Sept 19-22 : wrap up in Tana

Sept 22 : depart for USA

Tags

6 Argos GPS solar @

2 Argos GPS battery @

8 e-obs @

1 e-obs base station @

Sophia’s budget: $7600

$2,500 – flights