## Timeline
| Calendar year | 2023
| Month | JULY | [11 empty] | AUGUST | [30 empty] | SEPTEMBER
| Day | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Location | Task
Antananarivo | configure devices & pack field gear | bar: JULY 20 to JULY 24
Travel | travel to Analambotaka | bar: JULY 25
Analambotaka | 2 GPS solar argos Pteropus | bar: JULY 26 to JULY 30
Moramanga area | 2 GPS VHF each subpop x 4 subpops Pteropus | bar: JULY 31 to AUGUST 12
Travel | travel to Tana | bar: AUGUST 13
Antananarivo | unpack and repack field mission | bar: AUGUST 14 to AUGUST 16
Travel | travel to Ankarana | bar: AUGUST 17 to AUGUST 19
Ankarana | Ankarana - 2 GPS solar argos Pteropus | bar: AUGUST 20 to AUGUST 29
Travel | travel to Nosy Hara | bar: AUGUST 30 to AUGUST 31
Nosy Hara | 2 GPS solar argos Pteropus | bar: SEPTEMBER 1 to SEPTEMBER 7
Nosy Hara | 2 GPS battery argos Eidolon | bar: SEPTEMBER 8 to SEPTEMBER 14
Travel | travel to Tana | bar: SEPTEMBER 15 to SEPTEMBER 17
Antananarivo | unpack field mission & repack | bar: SEPTEMBER 18 to SEPTEMBER 20
Travel | travel to Moramanga area | bar: SEPTEMBER 21
Moramanga area | visit to download data (optional) | bar: SEPTEMBER 22 to SEPTEMBER 25
Travel | travel to Tana | bar: SEPTEMBER 26
Antananarivo | unpack & wrap up | bar: SEPTEMBER 27 to SEPTEMBER 29
Travel | depart for USA | bar: SEPTEMBER 30

## Budget
Lotek & e-obs | [6 empty] | GHF Grant Budget |  | Total | 7600 | Remaining | 181
Item | Brand | Link | Cost per Item | Count | Total | Grant
Solar VHF | e-obs digital telemetry | https://e-obs.de/products.html | 1275 | 1 | 1275 | GHF | Item | Cost
Battery Argos/GPS | Lotek | https://www.lotek.com/products/pinpoint-gps-argos/ | 1900 | 6 | 11400 | Biota | Flight | 2200
Solar Argos/GPS | Lotek | https://www.lotek.com/products/pinpoint-gps-argos-solar/ | 2300 | 2 | 4600 | Biota | tech | 4019
Solar VHF | e-obs digital telemetry | https://e-obs.de/products.html | 1275 | 7 | 8925 | Biota | in-country travel for field team | 500
Base Station | e-obs digital telemetry |  | 1830 | 1 | 1830 | GHF | Tana lodging (20 days at $20 per day) | 400 |  | total | 7419
Tracking Setup for dropped loggers | e-obs digital telemetry |  | 444 | 1 | 444 | GHF | Misc | 300
Lotek reader/programmer/charger | Lotek |  | 290 | 1 | 290 | GHF
Yagi antennae |  |  | 180 | 1 | 180 | GHF
| Biota total | 24925
| GHF total | 4019
| total | 28944
Lotek only | [6 empty] | GHF Grant Budget |  | Total | 7600 | Remaining | 1340
Item | Brand | Link | Cost per Item | Count | Total | Grant
Battery Argos/GPS | Lotek | https://www.lotek.com/products/pinpoint-gps-argos/ | 1900 | 6 | 11400 | Biota | Item | Cost
Solar Argos/GPS | Lotek | https://www.lotek.com/products/pinpoint-gps-argos-solar/ | 2300 | 2 | 4600 | Biota | Flight | 2200
Battery VHF | Lotek |  | 1400 | 7 | 9800 | Biota | tech | 2860
reader/prog/charger | Lotek |  | 290 | 1 | 290 | GHF | in-country travel for field team | 500
Command Unit | Lotek |  | 990 | 1 | 990 | GHF | Tana lodging (20 days at $20 per day) | 400 |  | total | 6260
Yagi antenna | Lotek |  | 180 | 1 | 180 | GHF | Misc | 300
Battery VHF | Lotek |  | 1400 | 1 | 1400 | GHF
| Biota total | 25800
| GHF total | 2860
| total | 28660
Microwave telemetry & e-obs | [6 empty] | GHF Grant Budget |  | Total | 7600 | Remaining | 471
Item | Brand | Link | Cost per Item | Count | Total | Grant
Solar Argos/GPS 17g PTT | Microwave Telemetry, Inc. | https://www.microwavetelemetry.com/solar_argos_gps_17g_ptt | 4200 | 6 | 25200 | Biota | Item | Cost
Battery VHF | e-obs digital telemetry | https://e-obs.de/products.html | 1275 | 7 | 8925 | Biota | Flight | 2200
Base Station | e-obs digital telemetry | pers. Comm. | 1830 | 1 | 1830 | GHF | tech | 3729
Tracking Setup for dropped loggers | e-obs digital telemetry | pers. Comm. | 444 | 1 | 444 | GHF | in-country travel for field team | 500
Battery Argos/GPS | Lotek | pers. Comm. | 1900 | 2 | 3800 | Biota | Tana lodging (20 days at $20 per day) | 400 |  | total | 7129
Yagi antenna |  |  | 180 | 1 | 180 | GHF | Misc | 300
Battery VHF | e-obs digital telemetry |  | 1275 | 1 | 1275 | GHF
| Biota total | 37925
| GHF total | 3729